## Working action plan
ACTION PLAN RAG RATING ACTIONS AND SUCCESS MEASURES | [7 empty] | Green: Good progress was made on this action. | the action was completed with outcomes or impacts as (or very close
to) predicted/desired;
This is a template for a working action plan arranged by theme with sections for tracking rag rating, barriers, changes and facilitators which will help you to build your narrative on process, success and barriers | [8 empty] | no further work is needed on this action.
[8 empty] | Amber: Partial progress was made on this action | the action has begun but is incomplete;
Please feel free to adapt in any way that is useful | [8 empty] | the action was completed but the outcomes or impacts were not as predicted/desired;
further work is needed to complete the action or to obtain the desired outcome or impact.
Following tabs include formats for your application that might be useful, incuing showing RAG rating over time, and RAG rating actions and success measures for a more nuanced look at progress. | [7 empty] | Red: No progress was made on this action. | the action was never undertaken;
the action was started but was permanently discontinued;
further work is needed to begin the action or to revise the approach.
FOR DEPARTMENTAL USE ONLY
Ref | OBJECTIVE | RATIONALE/EVIDENCE/BASELINE DATA | ACTIONS | TIMESCALE | RESPONSIBILITY | SUCCESS MEASURE | NOTES | BARRIER | FACILITATOR | CHANGE TO ACTION | RAG [XX date] | RAG [XX date] | RAG [XX date] | RAG [XX date] | RAG [XX date]
PRIORITY/SECTION XX
PRIORITY/SECTION XX
PRIORITY/SECTION XX
PRIORITY/SECTION XX
PRIORITY/SECTION XX

## AP for App (RAG over time)
ACTION PLAN RAG RATING ACTIONS AND SUCCESS MEASURES | [5 empty] | For amber and red actions, and assign thematic barriers to aid in signposting to the relevant narrative discussion | If an action changed over the course of the period you can briefly indicate this here
This formatting show RAG rating as a journey and will allow you to demonstrate visually how you tackled your actions over the award period, demonstrating how you have developed and delivered your objectives and action plan as a live document over time. | [8 empty] | R | No progress was made
[9 empty] | A | Partial progress was made
[9 empty] | G | Good progress was made
Colour Code columns J to N, deleting columns as appropriate (you may want 3 point of data or fewer)
Assign a barrier in column G, and notes in column P to aide in narrative composition
[9 empty] | RAG RATING OVER TIME | [5 empty] | NOTES: FOR DEPARTMENTAL USE ONLY
Ref | OBJECTIVE | RATIONALE/EVIDENCE/BASELINE DATA | ACTION/ACTIONS | TIMESCALE | RESPONSIBILITY | BARRIER | CHANGES TO ACTION | SUCCESS MEASURE | 2018–19 | 2021–22 | 2022–23 |  |  | Notes | Detail here any contextual information that will help you write your narrative
[11 empty] | MT | HT | TT
1. IMPROVING WORKPLACE ORGANISATION AND CULTURE
1.1 | Increase awareness of Equality, Diversity and Inclusivitiy in the Department and encourage involvement by a wider range of staff and students | We do not currently monitor staff awareness and perception of EDI. Our mini-survey suggested that staff appreciate being consulted and would like to be more involved. When we last called for new members of the EDI committee, we had no student volunteers | Regular articles in the Departmental E-newsletter highlighting EDI activities. | 2018–2023 | Communications Officer |  | Wording changed from >90% of staff and students are aware of Athena Swan activities within the department | >90% of staff and students are aware of departmental events that encourage equality, diversity and inclusivity across our department | R | A | A | A | A
|  |  | Minutes of the EDI Committee to be made available on staff webpages. | 2018–2023 | HR Lead/Communications Officer |  |  |  | R | G | G | G | G
|  |  | Questions about awareness of and involvement in EDI activities to be included in the Staff Survey. | 2018–2023 | AS Lead | Steps to invest in capacity of Comms team to invest in these actions, lack of systematic way of monitoring staff awareness perception | Wording changed from >90% of staff and students are aware of Athena Swan activities within the department | >90% of staff and students are aware of departmental events that encourage equality, diversity and inclusivity across our department | R | A | A | A | A
|  |  | Communications Officer to prepare an annual review about EDI activities in consultation with the EDI committee (annually from Oct 2018). | 2018–2023 | Communications Officer/EDI Lead |  | Reviews provided termly to both EDI and Senior Management Committee |  | R | G | G | G | G
1.2 | Broaden the focus of the EDI committee to incorporate aspects other than gender into our remit of improving the workplace for all staff | There is a high proportion of women in our Department and the results of our 2016 and 2018 Staff Surveys show significant differences between women in many of the responses. We wanted to make sure that initiatives that were started in response to fostering women's careers, were also considered with respect to their impact on men's careers and other aspects of Equality and Diversity, such as ethnicity and disability. The Departmental Management Committee has supported this broadening of emphasis. | Use outreach activities as a source of positive images of female and male (incl. all genders) role models in the Department by Publishing successful women in science and celebrate their efforts regularly (newsletters, social media, Town Hall meetings) | October–December 2018 | HoD/EDI Chair |  |  | >90% of staff and students are aware of departmental initiatives to promote equality, diversity and inclusivity across our department | R | A | A | A | A
|  |  | Produce an EDI Annual Report describing the diversity of staff working in the department. EDI Chair provides termly updates to the Management Committee | December (2020) | EDI Chair/HR Lead | Status of report needs monitoring and preparation, requires regular reviewing of milestones |  | Department has accurate EDI data by role and year in preparation for our next Athena SWAN submission. Management Committee meeting minutes to show the EDI lead’s updates | R | A | A | A | A
1.3 | Improve the workload distribution within the EDI committee | We carried out a recent poll of all EDI committee members and although 80% of members were happy with how the EDI committee is organised, all identified the need for mechanisms for ensuring fair sharing of the workload which 60% felt was uneven. | Rotate the EDI Chair position every 3 years. | every 3 years | EDI Chair |  |  |  | R | G | G | G | G
|  |  | Review EDI workload annually, including gender balance. | 2019-01-01 | AS Lead |  |  | >80% of the EDI committee reporting that the EDI workload allocation is fair in 2020 and 2022, and 2023 EDI poll. | R | G | G | G | G
|  |  | Consider creating separate working groups to focus more on specific issues, e.g. students, Grade 5/6 Researchers, outreach. | (October–December 2018 | EDI Committee |  |  | Sub-committees have been created to ensure support for students, ECR, professional staff and HR team to focus on data collection support | R | G | G | G | G
1.4 | Increase uptake of Shared Parental Leave | uptake of SPL has been low (1 man since 2014) reflecting the national picture. We are keen to promote SPL by making clear and well- advertised information available to all staff | Increase enquiries about and uptake of the Shared Parental Leave scheme (SPL) by updating the departmental website and increase visibility and writing an article for the E-newsletter for the next round of staff members to take SPL | 01/10/2018–2022 | Communications Officer |  |  | At least two more staff to have taken SPL by 2022. | R | G | G | G | G |  | Since 2018, 2M and 1F have taken up SPL
1.5 | Increase number of Department-wide social events to enhance the cohesion of the Department and ensure staff feel integrated into the social life of the department | As the Department grows we need to adapt our social activities to meet the needs of a larger staff group. A Staff Away Day is planned for August and a Christmas Party for December, but the Events Committee are exploring other activities in between, such as a Quiz Night | Ensure that social events are planned and publicised well in advance | 2018–2022 | Events Committee, Communications Officer |  |  | Staff garden party, Anniversary celebration, student socials, OVG team events | R | G | G | G | G
|  |  | Ensure that the Events Committee has an allocated budget to support their programme | April 2018–2022 | HoF, Communications Officer | Engagement of the Events Committee to engage in EDI, lack of communication between the committees within the department |  |  | R | A | A | G | G
1.6 | Increase opportunities for staff to gain experience of serving on internal and external committees | Only 57% of our ECR, 37% of our Researchers and 33% of our students are currently serving on departmental committees. Since committee experience is an essential part of the RoD criteria, it is important that we open up the opportunity to serve on committees to a greater proportion of our staff. We do not currently have a standard process for making nominations to committees. | Update information about current committee membership |  | Committee leads to liaise with Communications Officer | Time constraint/ capacity to update websites/ intranet regularly |  | All staff considering applying for promotion via the RoD able to demonstrate evidence of internal and/or external committee membership on their application | R | R | R | G | G
|  |  | Introduce a standard process for making internal and MSD committee nominations and publish this on the staff webpages and share process with staff via the E- newsletter | 2019-04-01 | HoD and Management committee and Communications Officer | Relevance of MSD committees and communication of their committee processes and structure | Limiting this action to departmental committees rather than MSD committees | Committee nomination process written and available on the website and E-newsletters. | R | R | R | G | G
|  |  | Survey staff to document interest in serving on committees by role and gender and Include questions about committee membership (actual and interest) | January 2020 and January 2022 | AS Lead | Reaching out to staff members efficiently to conduct survey |  | Peakon implementation in 2022 | R | R | R | A | A
1.7 | Encourage reporting of Bullying and Harassment cases to the Bullying and Harassment advisors | Our 2018 Staff Survey showed that although we had a relatively low number and rate of staff who had witnessed or experienced bullying and harassment (5F/1M), none of these episodes were reported to the Bullying and Harassment Advisors. Bystander training may help to encourage other staff members to advise colleagues to access support through the Bullying and Harassment advisor | Create a list of the ‘local’ Bullying and Harassment advisors for each site |  |  |  |  | Awareness of Bullying and Harassment Advisors increased to 85% of staff in the 2020 and 2022 Staff Surveys. | R | G | G | G | G
|  |  | Offer bystander training to all staff and students | 2018-11-01 | HR Lead | During Covid, no remote training was offered |  |  | R | R | R | G | G
|  |  | Include questions in the next Staff Surveys to find out whether people feel that reported episodes of bullying and harassment have been dealt with appropriately | 2020-01-01 | AS Lead |  |  | At least 50% of bullying and harassment experiences reported in Staff Survey also reported to our Bullying and Harassment Advisor | R | G | G | G | G
|  |  | Continue to participate in National Anti-Bullying Week campaigns and to run National Anti-Bullying Week campaigns, including featuring articles in newsletter | Every November | Communications Officer |  |  |  | R | G | G | G | G
1.8 | Increase involvement and visibility of staff in outreach activities and their value as positive female and male (incl. all genders) role models | Our 2018 Staff Survey found that although 53% of our A&R staff (53%F/55%M) had taken part in an outreach activity in the last 12 months, a further 30% (26%F/36%M) would like to. Amongst PSS staff 33% (29%F and 50%M) were involved in outreach and a further 25% (26%F/17%M) would like to | Collect information about planned outreach activities before they occur by reaching out to PI's and previous organisers of outreach activities then publicise opportunities to participate in outreach activities well in advance | October 2018–2022 | Communications Officer |  |  | 80% of our A&R staff (80%F/80%M) involved in outreach in the 12 months prior to the 2020 and 2022 Staff Survey. 60% of PSS staff involved in outreach (60%F/60%M) in the 12 months prior to the 2020 and 2022 Staff Survey | R | G | G | G | G
|  |  | Make outreach activities are accessible to all genders by varying the time of the day and day of the week. This will ensure that all staff are offered the opportunity to attend | [5 empty] | R | G | G | G | G
|  |  | Use outreach activities as a source of positive images of female and male (incl. all genders) role models in the Department by Publishing successful women in science and celebrate their efforts regularly (newsletters, social media, Town Hall meetings) |  | Communications Officer |  |  |  | R | G | G | G | G
|  |  | Ask line manager to include questions about outreach activities on PDR's for all staff and record whether staff would like to be involved. Then collate outreach activity information from PDRs and link staff requesting outreach involvement with the Communications Officer | Line managers- August 2018–2019 HR- 2019 October | HR, Line managers | Low uptake of PDRs (which is a priority currently being addressed elsewhere on the plan). Also, there is currently no mechanism for recording outreach activities on the system used to manage the PDRs which makes this currently impossible. | Line manager to collate that information to report back, Peakon (survey tool) to allow data collection more easily |  | R | A | A | N/A | N/A
2. IMPROVE THE SELECTION, INDUCTION AND INTEGRATION OF DPHIL STUDENTS IN THE DEPARTMENT
2.1 | Increase the number of Paediatrics DPhil students | We have a low number of applications for our Paediatric DPhil programme 37 (19F/18M) during 2014–2017 (6–15 per year). This compares to ~200 students/ year and 10 applicants/place for WIMM DPhil studentships. We also have a low number of applicants/place (1.5–2) compared to the University average of 6 applicants/place. | Consolidate all of the information about DPhil research opportunities and how to apply within the Department into a dedicated, easy to access section of the Departmental website to increase promotion | 2019-10-01 | Communications Officer |  |  | number of DPhil applicants 15–20 every year | R | G | G | G | G |  | DPhil applicants have exceeded the target - 24 this year. This is a real success given that historically, applicants were from EU countries - and that these have had to be replaced post-Brexit.
|  |  | Advertise DPhil opportunities on Find-a-PhD.com. | 2019-10-01 | Chair Graduate Studies Committee and Graduate Studies Administrator |  |  |  | R | R | G | G | G |  | Very high CTR rate. Subscription will continue next year - with campaign to start a week before in October 2023.
|  |  | Update PIs’ webpages and include details of available DPhil projects to encourage potential and eligible Dphil students to apply for external fellowships in research grant applications and increase the funding for DPhil places | 2019-03-01 | PI's with help from Communications Officer | We need PI's input to update website. Problem standardising how to communicate PhD vacancies, as these comprise various types - national/locally-awarded/external etc. |  |  | R | A | N/A | N/A | N/A | Action Point has been changed to N/A as there as the department now has multiple publication mechanisms for DPhil vacancies (a dedicated page on the website, FindaPhD subscription). This has resulted in a marked uptake of applicants for 2022-23. | PhD studentships already publicised through PI's social media accounts + website + FindaPhD.com. Given this, is it necessary to have the studentships publicised on the PI's Paediatric pages?
2.2 | Increase DPhil student events & networking | Our previous Staff Survey 2016 had shown that only 56% of women and 50% of men felt integrated into the Department with similar results across A&R staff, PSS staff and students | Promote the DPhil Network to reach all DPhil students | October 2018–2022 | Graduate Studies Administrator, Communications Officer |  |  | More than 70% (70%F/70%M) attending DPhil Network events (both online and in-person) | R | G | G | G | A
|  |  | Trial new types of networking events, e.g. evening social events and scientific events. |  | Graduate Studies Administrator (work with students) |  | Due to post-Covid patterns of engagement, action has been changed to include participation in online events. | At least 4 DPhil Network events each year by October 2019. | R | G | G | G | G
|  |  | Encourage attendance of events for DPhil students by letting PIs know when events will be happening, so students feel able to leave the lab/office to participate. |  | Communications Officer | cc PI mailing list when events are published. | Action added as PIs encouragement of student attendance identified as a motivator for participation. | More than 70% (70%F/70%M) attending DPhil Network events (both online and in-person) | N/A | N/A | N/A | A | A
3. IMPROVE CAREER AND DEVELOPMENT OPPORTUNITIES FOR ALL STAFF
3.1 | Work towards achieving gender balanced recruitment | Data on the actual composition of interview panels is not currently reviewed by the EDC. Although we achieved increasing recruitment of women 2014–2016, the number of women applying and appointed in fell in 2017. While the increased number of men recruited in 2017, helped to rebalance what had been a predominantly female A&R workforce. We ask all PIs to complete recruitment training every 4 years. A recent review showed not all PIs have done so. | Continue to make mixed gender interview panels mandatory and monitor compliance with this by only approving interview panels which contain both female and male members and to compile an annual report for the EDI Committee on compliance | 2018–2022 | HR Lead | Existing gender balance of staff members and their roles/ seniority |  | All interview panels to be mixed gender between 2018 and 2023 | R | G | G | G | G
|  |  | Ensure that all PIs and other panel members have received recruitment training. Recruitment Training is renewed every 4 years | September annually | HR Lead | No access to people's training records | Regularly reinforcing managers to undertake relevant training | All PIs to complete recruitment training every 4 years. Putting process in place at stages of recruitment process to remind panel members of training | R | A | A | A | A | Managers will be asked in new PDR form to confirm they have completed this.
3.2 |  | We did achieve our 2015 AS aim of increased uptake of training courses by our staff only by 25% (from 30 to 41/year) and 70% of our male A&R staff had done no training courses in the last year suggesting that we are not publicising these well enough given that the 100% of males in our 2018 Staff Survey felt they had time to undertake training | Update web pages on the Departmental website and the staff webpages with links to a range of training providers. | 2018-10-01 | Communications Officer |  |  | Webpages updated with increased visibility on the main Departmental website and enhanced links created. | R | G | G | G | G
|  |  | Include a section on career development opportunities in every E-newsletter as well as reminders of upcoming opportunities in the E- message | ongoing from August 2018 | Communications Officer |  |  |  | R | A | A | G | G
3.3 | Increase the visibility and accessibility of training opportunities for all staff | Since the Staff Learning Scheme was established there have been only 22 applications (2014–2017) nearly all from PSS staff- only 5 from A&R staff suggesting that A&R staff are likely to be unaware of the existence or purpose of the Fund. An informal poll or Researchers and ECR suggests that this is the case. | Publicise the Staff Learning Scheme as a source of funding for external training together with the deadlines for application using an Article explaining the purpose of the Staff Learning Fund and how to apply to be written for the E-newsletter and then posted on the website | 2018-10-01 | Communications Officer |  |  | >90% aware of Departmental Staff Learning Fund by 2020 survey. | R | G | A | A | A
|  |  | Promote opportunities to sign up for the Communities of Practice University scheme. Communications Officer to signpost this in weekly and monthly coms update before May 2023. Highlight in induction pack for new starters. | Oct 2018–2022 | Communications Officer/HR Lead |  |  | >90% of researchers agree that they have opportunities to participate in formal and/or informal training at work (Staff Survey 2021 and 2023). | R | G | A | A | A
3.4 | Ensure all staff every year have a PDR which is useful to them | We need to maintain high completion rates and ensure these PDRs are high quality. Since the online system is new and introduced <9 months ago, it is important that we obtain feedback both from appraises and appraisers on the new PDR system to ensure the high quality of the process and make adjustments as needed | Maintain high PDR completion rate By sending reminders when the Annual PDR is due and request feedback once the PDR is complete by running a mini-survey for feedback and improved PDR process based on feedback | September 2018–2022 | HR Lead to send reminders and EDI Committee with AS Lead and HR Lead for survey. HR has created a Town Hall PDR session and will roll out HR Master-class session to all Paed groups in 2023. | Buy-in from line managers to spend time on PDR, system is not very intuitive, lack of enforcement mechanism (incl. unable to monitor completion rate for PDR completed outside of the departmental system), uncertainty on how to conduct PDR. |  | Steady increase in PDR completion rate in 2023 from previous years. Steady increase in report that PDR is useful in 2023 survey. | R | A | A | A | A | Awaiting next PDR cycle - September 2023
|  |  | Provide PDR training for new line managers by send out the POD PDR guide for all line managers - depending on the outcome of the mini-survey | 2019-07-01 | HR Lead |  |  | 80% of new line managers to have completed PDR training. | R | A | A | A | A
4. SUPPORT CAREER PROGRESSION FOR RESEARCHERS
4.1 | Increase Mid-Career Researcher (ECR) Fellowships | We had no applications for conferment of the title of University Research Lecturer from ECRs during 2014–2017. Although some of our ECRs would not yet be eligible, this indicates that we need to do more to encourage Researchers to consider applying for title via the RoD and line managers to flag this during the PDR | Ensure all Researchers and CRFs have access to information about external intermediate level fellowships by creating a dedicated career development section of the website for clinical and non-clinical researchers, including: a list of fellowship opportunities and links to relevant websites and regularly update on the Departmental website. Flag upcoming opportunities via the E- newsletter | 2019-01-01 | Communications Officer |  | Speak to funders of existing new Departmental Fellowships to explore opportunities for further fellowships. | Increase the number of staff holding ECR fellowships from 7 to 9 by May 2022 with a balanced number of women and men in post. | R | G | G | G | G
|  |  | Arrange pre-fellowship application review by senior PIs by addressing fellowship applications as part of the PDR for all Researchers and CRFs. | 2019-01-01 | HoD/DA to remind Pis |  | Extended to ECR | Increase the number of female and male Researchers and CRFs submitting externally- funded ECR applications from 4 in 2014–2017 to 6 in 2018–2022. | R | G | G | G | G
|  |  | Arrange mock interviews for all staff short-listed for fellowships | 2019-01-01 | PIs |  |  |  | R | G | G | G | G
|  |  | Funders of Departmental Fellowships to be approached by relevant PIs and HoD | 2019-01-01 | PIs HoD |  |  |  | R | G | G | G | G
4.2 | Increase support for Researcher and ECR career progression | The Researcher Network is still at an early stage We had no applications for conferment of the title of University Research Lecturer from ECRs during 2014–2017. Although some of our ECRs would not yet be eligible, this indicates that we need to do more to encourage Researchers to consider applying for title via the RoD and line managers to flag this during the PDR. No ECR were returned in REF 2014 as there were none in post at that time. Knowledge of the process amongst the ECRs is therefore low and only 1 (1F) has experience of being REF returnable in 2014 in her previous post. Senior members of staff have good understanding of how to prepare for the REF and how to have a strong return, which needs to be communicated to ECRs | Further develop the potential of newly formed Researcher Network and continue to host informal discussions | 2018–2022 | Researcher Champion | Was on hold during pandemic. Researcher Network no longer used - ECR networking to take place via socials. |  | > 80% of people who respond to a poll informal Research network event found it helpful | R | R | R | G | G
|  |  | Evaluate the role and benefits of the Researcher Network to see if adjustments are needed to respond to Researchers needs by collect feedback from Researchers/ ECR about the role and value of the Network and any changes they would like via a mini-survey and then researcher Champion to write a short annual report for the EDI Committee about activities of the Network and the results of the mini-survey | 2019-05-01 | AS Lead, Researcher champion, HR Lead | On hold due to pandemic. |  | > 80% Researchers and ECR staff happy with the career support they receive (mini survey 2019). At least 1 application/year to the RoD for consideration for conferment of the title of University Research Lecturer. At least 2 ECR REF-returnable. | R | A | A | A | A
|  |  | Ensure career progression discussed at the PDR. and produce an annual report for the EDI Committee | 2018-09-01 | HR Lead/team |  |  |  | R | A | A | A | A
|  |  | Ensure all Researchers/ ECR have access to a mentor by allowing information about mentorship and how to access the Departmental ECR mentorship scheme to be easily visible on the Departmental website and staff webpage and highlighted in the E- newsletter and then Collect information from the 2020 and 2022 Staff Survey about how many staff have a mentor/ know about the mentorship scheme/ don't have a mentor but would like on | Every month oct 2019 | Communications Officer, HR Lead/AS Lead |  |  |  | R | G | G | G | G
|  |  | Ensure ECR are well informed about the next REF by inviting all staff eligible (or potentially eligible) to be returned in the next REF to attend a REF workshop | April 2019, April 2020 |  |  |  |  | R | G | G | G | A | It was agreed that we revisit this nearer the next REF.
4.3 | Continue to develop and optimise grant application support for Researchers and ECRs | review of our data for 2014–2017 showed that there had been only 10 grant applications by Researchers or ECRs during 2014– 2017. 1 ECR (F) was named as a co- applicant but otherwise no ECR or Researchers were named co- applicants. None of the 4 applications by Researchers was successful | Create a dedicated career development section of the website, including information about applying for research grants and links to funding bodies and to help compile a list of research grant opportunities and links to relevant websites and regularly update on the Departmental website and flag upcoming opportunities via the E- newsletter to ensure all Grade 7 and above A&R staff have access to information about research grant applications | 2019-01-01 | Communications Office, Research champion |  |  | Higher success rate for grant applications by ECR (>50%). And Increased number of research grant applications with Researchers/ECR as named applicants. | R | G | G | G | G
|  |  | Arrange pre-research grant application review by senior PIs and remind PIs to consider including Researchers/ECR as co- applicants on research grants. | 2019-01-01 | Research Champion |  |  |  | R | G | G | G | G
|  |  | Ensure all ECR have access to a Mentor and grant writing workshop and collate information about grant writing workshops for Researchers in MSD, the University and beyond the University and post these on the Career Development section of the website | 2019-01-01 | Communications Officer |  |  |  | R | G | G | G | G
|  |  | Formal review of impact of grant support system on funding success through arranged pre-research grant submission review | 2019-01-01 |  |  |  |  | R | A | A | A | A
5. SUPPORT CAREER PROGRESSION WITH BALANCED GENDER REPRESENTATION ACROSS THE ACADEMIC CAREER PIPELINE FOR CLINICIANS AND NON-CLINICIANS
5.1 | Support clinical academics to continue with a scientific research career. | The career pipeline for clinician scientists is insecure because it is entirely dependent upon highly competitive externally-funded fellowships. Without bridging support for the Department, clinician scientists are at high risk of leaving science and returning to full-time NHS jobs | HoD/HoF to explore options for bridging funding between fellowships. | May 2018–2022 |  |  | Is and HoD to proactively plan and support Clinician Scientists to apply for Senior Fellowships. | Support at least 2 (1F/1M) Clinician Scientists to obtain a Senior Fellowship (October 2020 | R | G | G | G | G
|  |  | Annual Paediatric Research Day to include a balance of clinical and non- clinical scientists as well as balance by gender and ensure that the work of clinical academics at all levels of training and experience (CRFs, Clinical Lecturers and Clinician Scientists) is publicised on the website and in the E-newsletters to Ensure the work of female and male clinical academics are visible as role models in the Department. | annually in August 2018–2022 | Graduate Studies Administrator/DA, Communications Officer |  |  |  | R | G | G | G | G
5.2 |  | The proportion of women holding the Professor title has not increased since 2014 and is not consistent with our pipeline. | Identify all eligible candidates for RoD schemes annually and encourage to apply by inviting them to discuss submitting an application | March 2018–2022 | HoD and Pis |  |  | 2 successful female applications for Professor title by 2022. 2 successful female applications for AP title by 2022. 2 successful female applications for URL title by 2022. | R | G | G | G | G |  | This action has now been completed. Discuss how to move forward with this. Continue that professorial ratio between M and F professors remain equal?
|  |  | Provide internal support for RoD applicants to strengthen applications By establishing a gender- balanced internal RoD committee to review applications prior to submission and provide advice. | April 2018–2022 | HoD, Hof |  |  |  | R | G | G | G | G
|  |  | Offer mentorship for unsuccessful RoD candidates to support them to meet the requirements | Sept 2018 – 2022 | HoD to ensure all unsuccessful candidates are offered mentorship by a senior member of the Department |  |  |  | R | G | G | G | G
5.3 | Increase the number of female applicants to new senior academic (Professor/AP) appointments | There are currently fewer women Professors than male Professors (1F/3M) although the number of APs is currently balanced (1F/2M). Opportunities to recruit senior academics to our Department arise infrequently due to the small size of the Department but we have approval to recruit to 2 senior (Professor/AP) posts in 2018–2019) | Ensure that the recruitment pool includes women. And that recruitment opportunities are uploaded to the website which will also include new posts and outcomes. Ensure that all Pis promote the recruitment and encourage suitably qualified women to apply | 2018–2019 | PIs |  |  | Appointment of 2 Professors (at least one female) during the 2018–2019 recruitment round. For 2022–23 50% female recruitment for senior academic posts. | R | G | G | G | G
|  |  | Ensure that there is a gender balanced shortlist/ longlist. | 2018–2019 | HoD/DA/HR Lead |  |  |  | R | G | G | G | G
5.4 | Increase the number of Researchers/ECRs on open-ended contracts | f | Continue annual review of all staff on fixed-term contracts and identify A+R staff with more than 4 years service and identify any staff who meet the criteria for moving to open ended/permanent . | September 2018, 2019, 2020, 2021, 2022 | HR Lead, HoF and HoD |  |  | Increase the proportion of male and female staff with more than 4 years’ service on open-ended contracts by 10% by 2022. Information and guidance about the process of moving from fixed-term to open-ended contracts clearly displayed on the staff webpages. | R | A | A | A | A | Division have now paused this. Awaiting decision to see if we will go ahead with this at departmental level.
|  |  | Create guidance for moving staff from fixed-term to open-ended contracts and share with Department. Via the e-Newsletter and website | 2018-09-01 | HR Lead and HoF to create, Communications Officer to circulate |  |  |  | R | A | A | A | A | Division have now paused this. Awaiting decision to see if we will go ahead with this at departmental level.
6. SUPPORT CAREER PROGRESSION FOR PROFESSIONAL AND SUPPORT STAFF
6.1 | Promote career opportunities and mentoring for Professional and Support Staff | The 2018 Staff Survey showed that although 100% PSS staff who had been offered a mentor found this useful, there were still many PSS staff (26%F and 50%M) who did not have a mentor and would like one. The survey also showed that PSS staff would like more events targeted specifically at them, and in particular career development and networking opportunities | Provide more support networks for PSS staff, including the University Careers Network mentorship scheme. Include relevant signposting via Departmental coms channels (Newsletter) termly. Will reference this on the staff intranet pages. Ongoing. | 2018–2023 | Hof/HR Lead/Communications Officer |  | Signposting | 90% of PS&S staff to have a mentor if they would like one (Staff Survey 2021 and 2023). >50% of PSS staff to attend career development events specifically designed for PSS staff (Staff Survey 2021 and 2023) >90% of PSS clear about career development opportunities (Staff Survey 2021 and 2023) Majority of PSS Staff aware of scheme in 2023 Staff Survey | R | G | A | A | A
|  |  | Promote initiatives to support PSS staff | 2018–2022 | Hof/HR Lead |  |  |  | R | G | A | A | A
|  |  | Encourage PSS staff to attend conferences on careers in HR, Finance, Department Administration and Development. | 2018–2022 | Hof/HR Lead | Workload and travel location (Paediatrics is based at the JR; conferences usually based in Oxford centre). |  |  | R | G | A | A | A
|  |  | Review what type of mentoring PSS staff require (e.g. job applications and interviews) and where there are gaps in mentor provision. And work with staff and other departments to meet the mentoring needs of PSS staff who would like general or specific mentoring | April 2019, | HoF/HR Lead | This action is now N/A as the way the Staff Survey is structured does not permit responses on the type of mentoring needed, but only if there is a need. Focus instead will be on establishing the demand level generally (see above). |  |  | R | R | N/A | N/A | N/A
|  |  | Promote opportunities to sign up for the Communities of Practice University scheme. Communications Officer to signpost this in weekly and monthly coms update before May 2023. Additional question on awareness of Communities of Practice to be included in the 2023 Staff Survey. | Before May 2023 (next Staff Survey) | Communications Officer/HR Lead |  |  |  | R | A | A | A | A

## AP for App (RAG Action+SM)
ACTION PLAN RAG RATING ACTIONS AND SUCCESS MEASURES
This will allow you to easily and visually deliniate between where
| actions were undertaken but success measures not/partially met, |  | RAG RATE ACTIONS |  |  | For amber and red actions, and thematic barriers to aid in signposting to the relevant narrative discussion (section 2.1) | If an action changed over the course of the period you can briefly indicate this here | RAG RATE SUCCESS MEASURES
| or actions where the action itself was not carried out |  | R: No progress was made |  |  |  |  | R: No progress was made
|  |  | A: Partial progress was made |  |  |  |  | A: Partial progress was made
Colour Code columns D and I |  |  | G: Good progress was made |  |  |  |  | G: Good progress was made
Assign a barrier in column G, and notes in column O to aide in narrative composition
Ref | OBJECTIVE | RATIONALE/EVIDENCE/BASELINE DATA | ACTION/ACTIONS | TIMESCALE | RESPONSIBILITY | BARRIER | CHANGES TO ACTION | SUCCESS MEASURE
PRIORITY XX / SECTION XX
PRIORITY XX / SECTION XX
PRIORITY XX / SECTION XX
PRIORITY XX / SECTION XX